## Product Backlog
Priority | User Story | Feature | Tasking | Status | Assigned
2 | As a user, I want to have any image projected onto the ball so that it conforms to its spherical shape. | Able to distort the image so that when it hits the ball it looks spherical | Pass image through barrel distortion method | In Progress | Ian
1 | As a user, I want to have any image projected onto the ball so that it conforms to its spherical shape. | Have the image show up at the correct location on the screen from webcam input | Correct for difference between webcam and projector locations | Accepted | Ian
1 | As a user, I want to be able to to track a ball in motion an continuosuly project an image onto it. | Ability to track the ball accurately | Circle Detection/Hough Circle | In Progress | Andrew
1 | As a user, I want a user interface so that I can control image selection and formatting settings. | Implement a GUI to control image selection and formatting settings. | Use Tkinter to develop the GUI. Implement a menu with various options and settings for the user to customize. | In Progress | Kevin
1 | As a user, I want a user interface so that I can select how far the camera and projector is to accurately project the image onto the ball. | Allow the user to set the distance from the projector to the screen, from the camera to the screen, the height of camera, the height of webcam's position, and possibly the angle of the projector. | Display input fields for the user to type in the distances and submit to the program. | Accepted | Kevin
1 | As a user, I want a user interface so that I can select how far the camera and projector is to accurately project the image onto the ball. | Set restrictions on the maximum and minimum values for the various distances. | Specify to the user the accepted values. Prevent the user from submitting values outside of the range. | Accepted | Kevin
2 | As a user, I want a user interface so that I can select how far the camera and projector is to accurately project the image onto the ball. | Allow the user to specify the distances in various units, including meters, feet, etc. | Implement a dropdown menu to allow the user to choose the distance unit. | Accepted | Kevin
5 | As a user, I want to be able to track multiple objects in order to increase the functionality. | Object reconization for multiple objects. | Be able to create multiple objects in code to project the chosen image(s) on the objects detected by the webcam. | Accepted | Andrew
4 | As a user, I want to be able to record a video of my projection. | Session Recording and File Creation | Start webcam recording and save file without breaking memory constraints. | Accepted | Alec
2 | As a user, I want to be able to select various image and animated formats. | Allow all image and animated file formats. | Look up all image and animated file extensions and allow support for these extensions. | Accepted | Kevin
2 | As a user, I want the ability to see all image files available in a directory when selecting an image to map onto the ball. This will be more convenient for me. | Display all image files through the file dialog. | Display all supported image file types in a single view. | Accepted | Kevin
3 | As a user, I want the GUI to be responsive and display the current status of the program. | Display the current status of the program. | Implement a status bar. | Accepted | Kevin
2 | As a novice user, I want a set of preselected images to choose from, so that I can test the program. | Ability for the user to choose from various preselected images. | Add in an array of preselected/default images. | Accepted | Kevin
2 | When an animated image is selected, its animation should be displayed | Handle animated formats. | Isolate frames of gif and store individual images into array that will be displayed sequentially. | In Progress | Zac
1 | When an animated image is selected, its animation should be displayed | Decided whether an image is animated or not. | Process image as animated or still depending of file type. | In Progress | Zac